✂

Beauty Salon Group

IT System — Full Project Roadmap

Phase 1  ·  Phase 2  ·  Phase 3

Stack: React + Vite  |  Firebase (Auth, Firestore, Hosting)  |  Git + GitHub Actions

Document version: July 2026

# 1. Project Overview

This document describes the complete IT system for managing a group of beauty salons (6–10 staff per branch). It covers all planned development phases, features built, features pending, and the recommended implementation timeline.

The system is built as a web application using React + Firebase, deployed via GitHub Actions on every push to the main branch.

## 1.1 Tech stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | React + Vite + Tailwind CSS | Web application (desktop & tablet) |
| Auth | Firebase Authentication | Email/password login, role-based access |
| Database | Firebase Firestore | Real-time NoSQL database |
| Storage | Firebase Storage | Photos, receipts, documents |
| Hosting | Firebase Hosting | Static web hosting with CDN |
| CI/CD | GitHub Actions | Auto-deploy on git push to main |
| Functions | Firebase Cloud Functions | Salary calc, reminders, reports |
| Analytics | BigQuery (linked to Firebase) | Heavy reports and payroll queries |

## 1.2 User roles

| Role | Access level |
| --- | --- |
| Owner | Full access to all branches, reports, payroll, settings |
| Manager | Full access to their branch; can edit staff and inventory |
| Receptionist | Customers, appointments, billing; read-only inventory |
| Stylist | View own schedule and attendance only |

## 1.3 Firestore collections (Phase 1)

| Collection | Description |
| --- | --- |
| customers/{id} | Customer profile, loyalty points, allergy notes |
| appointments/{id} | Booking details, stylist, status, date/time |
| invoices/{id} | Invoice lines, payment mode, discount, total |
| inventory/{id} | Product/item stock, reorder level, category |
| attendance/{id} | Daily employee attendance records |
| employees/{id} | Staff profile, role, branch, commission rules |

# 2. Phase 1 — Core Operations (Current)

Phase 1 covers the day-to-day operational modules needed to run a salon from day one: customer management, appointment booking, billing, basic inventory, and attendance tracking.

## 2.1 Built ✅

### Customer management

- ✅  Add new customer with name, phone, email, allergy notes

- ✅  Search customers by name or phone

- ✅  Loyalty points counter (auto-incremented on invoice)

- ✅  Total visit count (auto-incremented on invoice)

- ✅  Allergy / sensitivity notes displayed on customer record

### Appointment booking

- ✅  Book appointment: customer name, phone, service, stylist, date, time

- ✅  Filter appointments by status (scheduled / completed / cancelled / no-show)

- ✅  Stylist selector populated from employees collection

### Billing & POS

- ✅  Invoice creation with service catalog (9 services, configurable prices)

- ✅  Multi-payment modes: Cash, Card, UPI, Wallet

- ✅  Discount field per invoice

- ✅  Loyalty points earned on checkout (1 pt per ₹100)

- ✅  Customer visit count auto-incremented on invoice creation

- ✅  Today's revenue shown on billing page header

### Inventory

- ✅  Add items with name, category, SKU, quantity, reorder level, cost price

- ✅  Low-stock alert banner when any item is at or below reorder level

- ✅  Quick ± stock adjustment buttons on each row

- ✅  Filter by category or low-stock

### Attendance

- ✅  Mark employee present / absent / half-day per date

- ✅  Date picker to view/mark any past date

- ✅  Summary counts: present, absent, unmarked

### Auth & navigation

- ✅  Firebase email/password login

- ✅  Protected routes — redirects to login if unauthenticated

- ✅  Role profile loaded from employees collection on login

- ✅  Sidebar navigation with active state

- ✅  Sign out

### Infrastructure

- ✅  GitHub Actions CI/CD — auto-deploy to Firebase Hosting on push to main

- ✅  PR preview deployments (each pull request gets a unique preview URL)

- ✅  Firestore security rules (role-based: owner / manager / receptionist / stylist)

- ✅  Firestore indexes for all query fields

- ✅  .env-based Firebase config (secrets never committed to Git)

## 2.2 Pending ⏳

The following items are scoped for Phase 1 but not yet implemented:

### Customer management

- ⏳  Edit and delete customer record

- ⏳  Customer history view — all past visits and invoices in one screen

- ⏳  Allergy alert pop-up at appointment booking if customer has allergy notes

### Appointments

- ⏳  Update appointment status from the table (Complete / Cancel / No-show buttons)

- ⏳  Stylist double-booking conflict check with warning

- ⏳  Automated SMS/WhatsApp reminders via Cloud Function (24h and 1h before)

### Billing

- ⏳  Print or download invoice as PDF

- ⏳  GST line item on invoice (configurable rate, default 18%)

- ⏳  Loyalty points redemption at checkout (currently only earn, not redeem)

- ⏳  Refund / void invoice with reason

### Inventory

- ⏳  Edit and delete inventory item

- ⏳  Auto-deduct stock when an invoice is created (consumption per service)

### Attendance

- ⏳  Edit or correct a wrong attendance entry for the day

- ⏳  Monthly attendance summary per employee

### Employee management (UI)

- ⏳  Add / edit employees from the UI (currently must be done directly in Firestore)

- ⏳  Assign role, branch, and commission rate per employee

### General / UX

- ⏳  Loading skeleton states (replace plain "Loading..." text)

- ⏳  Empty state illustrations on first use

- ⏳  Mobile responsive sidebar (collapses on narrow screens)

- ⏳  Error boundary for Firestore connection failures

- ⏳  Seed script to pre-populate service catalog in Firestore

## 2.3 Phase 1 completion estimate

| Group | Items | Effort |
| --- | --- | --- |
| Employee add/edit UI | 1 screen | 1–2 days |
| Appointment status update | 1 feature | 0.5 days |
| Invoice PDF + GST | 1 feature | 1–2 days |
| Customer history view | 1 screen | 1 day |
| Stock deduction on billing | 1 feature | 1 day |
| Loyalty redemption | 1 feature | 0.5 days |
| Edit/delete (customers + inventory) | 2 features | 1 day |
| Mobile responsive sidebar | 1 feature | 0.5 days |
| Remaining UX polish | Multiple | 1–2 days |

Total estimated effort to complete Phase 1: 2–3 weeks.

# 3. Phase 2 — Salary, Operations & Reports

Phase 2 adds the back-office and management layer: staff payroll, supplier procurement, multi-branch administration, and business reporting. Target start: after Phase 1 go-live.

Estimated effort: 6–8 weeks.

## 3.1 Salary & commission engine

- •  Employee pay structure: base salary + commission + tips

- •  Commission rules configurable per service type or stylist tier

- •  Auto-calculate monthly salary from attendance and invoice data

- •  Deductions: late marks, unpaid leave

- •  Payslip generation (PDF download per employee)

- •  Payroll export to Excel / CSV for accounting software

- •  Advance payment tracking and deduction

Implementation note: Salary calculations run as Firebase Cloud Functions triggered at month-end, writing results to a salaries collection. BigQuery is used for cross-month aggregations.

## 3.2 Procurement

- •  Supplier directory with contact, payment terms, lead time

- •  Purchase order creation with line items and expected delivery date

- •  Approval workflow: Manager raises PO, Owner approves

- •  Goods received note — mark items received against a PO

- •  PO vs GRN matching with variance flag

- •  Supplier invoice logging and payment status tracking

- •  Price comparison across suppliers for the same product

- •  Auto-generate PO draft when stock hits reorder level

## 3.3 Multi-branch administration

- •  Central admin dashboard showing all branches side-by-side

- •  Branch-specific service menu and pricing overrides

- •  Inter-branch stock transfer requests and approval

- •  Cross-branch customer recognition — single customer record across branches

- •  Branch performance comparison in reports

- •  Manager can only see their own branch; Owner sees all

## 3.4 Reports & analytics

| Report | Description | Frequency |
| --- | --- | --- |
| Daily revenue | Revenue by branch and payment mode | Daily |
| Weekly summary | Revenue, new customers, top services | Weekly |
| Monthly P&L | Revenue vs salary vs procurement cost | Monthly |
| Service analysis | Most popular services, average ticket size | On demand |
| Peak hour analysis | Busiest times by day and branch | On demand |
| Stylist productivity | Revenue per stylist, services count, commission earned | Monthly |
| Customer retention | New vs returning ratio, lapsed customers (60+ days) | Weekly |
| Inventory consumption | Usage per service type, wastage, shrinkage | Monthly |
| Procurement spend | Spend by supplier, category, and branch | Monthly |

All reports exportable to Excel and PDF. Heavy aggregations use BigQuery via the Firebase → BigQuery streaming export extension.

# 4. Phase 3 — Growth & Automation

Phase 3 opens the system to customers directly and adds intelligent automation. Target start: after Phase 2 is stable in production.

Estimated effort: 10–14 weeks.

## 4.1 Online self-booking portal

- •  Customer-facing booking page (public URL, no login required)

- •  Real-time stylist and slot availability

- •  Service selection with duration and price shown

- •  Booking confirmation sent via SMS and email

- •  Customer self-cancellation with configurable cutoff window

- •  Waitlist join for fully booked slots

- •  Embed widget for salon's own website

## 4.2 Customer loyalty mobile app

- •  iOS and Android app (React Native)

- •  View loyalty points balance and tier (Bronze / Silver / Gold)

- •  Book and manage appointments

- •  View past visit history and invoices

- •  Receive push notifications for reminders and offers

- •  Refer a friend — earn bonus points

## 4.3 Packages & memberships

- •  Prepaid service bundles (e.g., 5 haircuts for ₹1,200)

- •  Monthly membership plans with included services

- •  Package redemption tracked at billing

- •  Expiry dates and balance alerts

- •  Bulk purchase discount rules

## 4.4 Advanced notifications & marketing

- •  Automated SMS/WhatsApp: 24h and 1h before appointment

- •  Birthday greetings with special offer coupon

- •  Lapsed customer win-back (no visit in 60 days)

- •  Post-visit feedback request (rating + comment)

- •  Bulk campaign sender for promotions

## 4.5 AI-based demand forecasting

- •  Predict busy periods from historical appointment data

- •  Auto-suggest staffing levels per shift and day

- •  Forecast inventory needs for the next 30 days

- •  Identify underperforming services for menu review

Implementation note: Uses Vertex AI (Google Cloud) trained on BigQuery historical data. Results surface as weekly digest in the manager dashboard.

# 5. Full Roadmap Timeline

| Phase | Module | Status | Est. Effort |
| --- | --- | --- | --- |
| Phase 1 | Customer management | Partial — edit/history pending | 3 days remaining |
| Phase 1 | Appointment booking | Partial — status update pending | 1 day remaining |
| Phase 1 | Billing & POS | Partial — PDF, GST, refund pending | 3 days remaining |
| Phase 1 | Basic inventory | Partial — edit, auto-deduct pending | 1.5 days remaining |
| Phase 1 | Attendance | Partial — edit, monthly summary pending | 1 day remaining |
| Phase 1 | Employee UI | Not started | 1.5 days remaining |
| Phase 1 | UX polish & mobile | Not started | 2 days remaining |
| Phase 2 | Salary & commission | Not started | 2 weeks |
| Phase 2 | Procurement | Not started | 2 weeks |
| Phase 2 | Multi-branch admin | Not started | 1.5 weeks |
| Phase 2 | Reports & analytics | Not started | 2 weeks |
| Phase 3 | Online self-booking | Not started | 3 weeks |
| Phase 3 | Customer mobile app | Not started | 4 weeks |
| Phase 3 | Packages & memberships | Not started | 2 weeks |
| Phase 3 | Notifications & marketing | Not started | 2 weeks |
| Phase 3 | AI demand forecasting | Not started | 3 weeks |

# 6. Development Setup & Deployment

## 6.1 Prerequisites

- •  Node.js 20+

- •  Firebase CLI: npm install -g firebase-tools

- •  Git + GitHub account

- •  Firebase project created at console.firebase.google.com

## 6.2 Local setup

1. Clone the repository and install dependencies:

git clone <your-repo-url>
cd salon-manager
npm install

2. Create .env file from the example:

copy .env.example .env
# Edit .env with your Firebase project keys

3. Start local dev server:

npm run dev
# App runs at http://localhost:5174

## 6.3 Firebase deployment

firebase login
firebase use your-project-id
firebase deploy --only firestore:rules,firestore:indexes
npm run build
firebase deploy --only hosting

## 6.4 Create first admin user

- •  Firebase Console → Authentication → Add user (email + password)

- •  Copy the new user's UID from the Authentication tab

- •  Firestore → Create collection "employees" → New document, ID = that UID

- •  Add fields: name (string), role: "owner" (string), branchName: "Main Branch" (string)

- •  Sign in to the app — you now have full owner access

## 6.5 GitHub Actions auto-deploy

Every push to the main branch automatically builds and deploys to Firebase Hosting. Pull requests get a unique preview URL.

Required GitHub repository secrets (Settings → Secrets → Actions):

| Secret name | Where to find it |
| --- | --- |
| VITE_FIREBASE_API_KEY | Firebase Console → Project Settings → Web app config |
| VITE_FIREBASE_AUTH_DOMAIN | Firebase Console → Project Settings → Web app config |
| VITE_FIREBASE_PROJECT_ID | Firebase Console → Project Settings |
| VITE_FIREBASE_STORAGE_BUCKET | Firebase Console → Project Settings → Web app config |
| VITE_FIREBASE_MESSAGING_SENDER_ID | Firebase Console → Project Settings → Web app config |
| VITE_FIREBASE_APP_ID | Firebase Console → Project Settings → Web app config |
| FIREBASE_SERVICE_ACCOUNT | Firebase Console → Project Settings → Service accounts → Generate key |

End of document